Hi Sandy –

Per our meeting today, below is a detailed summary of the schedule moving forward for the Old Meeting House project.

Work Plan / Site-Specific Quality Assurance Project Plan (SSQAPP) Preparation: By 6/6/2025

Work Plan / SSQAPP Regulatory Review / Approval: By 7/7/2025

Drilling / Soil Sampling: By 7/25/25

Groundwater Sampling: By 8/1/25

Data Review / Evaluation of Corrective Action Alternatives / Reporting: By 8/29/25

Report Regulatory Review / Approval: By 9/29/25

Corrective Action Plan (CAP) Preparation: By 11/10/25

CAP Regulatory Review / Approval: 12/10/25

30-Day CAP Public Comment Period: 1/10/26

I’ve accounted for up to 30-days for each regulatory review period, which is standard for these projects. However, we may save some time on the schedule if this review time is shortened.

Feel free to reach out with any questions.

Jeremy Roberts, P.G.

Principal / Environmental Program Manager  |  Jeremyr@kas-consulting.com

589 Avenue D , Suite 10 |  PO Box 787  |  Williston, VT 05495

www.kas-consulting.com  |  802 383 0486 x 1 p  |  802 383 0490 f