PROJECT MILESTONES AND TARGET SCHEDULE

Project Milestones to Date

- 10-21  Formed Committee

- 11-21  Selectboard update -approval of Department of Environmental Conservation (DEC)  forgivable loan up to $125,000

- 3-22   Contracted with Otter Creek and NRPC

- 4-22   Landowner Survey

- 5-22   Partial Draft (30%) of Preliminary Engineering Report (PER)  Completed

- 8-22   Obtained State Revolving Fund Loan ($48,000) for planning work

- 10-22 Announcement of $1.4 million ARPA appropriation

- 11-22  Identified target parcels to evaluate for  wastewater disposal

- 2-23    Selectboard update -identified target wastewater sites, status of feasibility study

- 4-23   Obtained permission for test pits on parcels4-23  Selectboard update -background information, potential loss of grants

- 7-23  Selectboard update -increase forgivable loan amount

- 11-23  Secured archeological clearance for completing test pits on 4 properties

- 12-23  Completed test pits on 4 properties

- 1-24  Announcement of $727K VT Community Recovery and Revitalization Program (CRRP) appropriation

- 1-24   Draft PER, 60% Complete

- 2-24   Community presentation-Allenholm parcel identified for investigation

- 2-24  Ongoing discussions with Vermont Land Trust concerning Allenholm conservation easement

- 3-24  Eliminated Keeler Bay as target service area due to transmission distance

- 3-24  Selectboard update -background information

- 8-24  Selectboard update, appoint S. Robinson to replace R. Brown on committee

- 9-24  Selectboard update -approval of potential ARPA and ACCD grants, Lavin property identified as potential target parcel, approval of $2500 for test pits

- 10-24  Revised DEC ($800,000) and ACCD ($239,000) grants

- 11-24  Negotiations begin to acquire Lavin property

- 12-24  Test pits on Lavin property, soils evaluation

- 6-25  Funding from DEC and ACCD, purchase of Lavin property

- 12-24  DEC approves PER

- 2-26  Wastewater project listed first on Grand Isle County Project Priority List

- 2-26  Vision Committee formed to solicit input on potential uses of Lavin property in addition to wastewater disposal

- 3-26  Contracted with Fitzgerald Environmental Associates to conduct a wetlands delineation on the Lavin property

- 3-26  Requested earmark funding from Welch and Sanders offices

- 4-26  Chose Weston and Sampson to undertake a “step two” engineering analysis, including, among other things,  investigation of additional wastewater disposal capacity, project design and cost analysis, permitting

- 5-26 Notification from Senator Welch’s office of nomination for a $1 million earmark

- 6-26  Preliminary wetlands delineation maps issued

Schedule (As of June 2026)

*	Spring, 2026     Delineate wetlands on Lavin property, additional test pits/soils evaluations

*	Summer, 2026  Project design